## Summary
ENPRO CONSULTANTS - WEBSITE WORK REPORT
Working session of 31 July 2026 (continued past midnight into 1 August 2026)
Project | Enpro Consultants - corporate website
Technology | React 18, TypeScript, Vite, Tailwind CSS, Framer Motion
Session start | 31 July 2026, 18:39
Basis of work | Client Rev-B documents dated 28 July 2026 (Landing Page, About Us, Services-01)
WORK COMPLETED
Client assets processed | 10 images received; 6 service photos and 12 icons extracted
Landing page | All five sections rebuilt to the client's content and layout instructions
New pages | About Us page and Services detail page created
Production bugs fixed | 7
Responsive work | Fluid typography, mobile viewport correction, unified spacing
Animation | Framer Motion scroll reveals across the landing page
Build status | Production build and type check passing
OVERALL PROGRESS | Approximately 75% of the website complete
Remaining work | Blocked mainly on client assets and decisions - see the Pending Items sheet

## Work Log
Date | Time | Category | Task | Description | Files / Deliverable | Status
31-Jul-2026 | 18:39 | Client Input | Client assets received | 10 reference images received from client (banners, editorial card collage, icon sheets, office photos) | src/assets/update images/ | Done
31-Jul-2026 | 19:00 | Analysis | Client documents reviewed | Three Rev-B documents analysed: Landing Page, About Us, Services-01 - content and visual instructions extracted | Requirement notes | Done
31-Jul-2026 | 19:30 | Analysis | Reference website studied | wordpress.themehour.net/builda - about-us and service-details page structures reviewed for layout patterns | Design reference | Done
31-Jul-2026 | 20:00 | Analysis | Existing codebase audit | Full project review - stack, structure, dead code and 6 production bugs identified | Audit report | Done
31-Jul-2026 | 22:46 | Assets | Service images extracted | Six individual service photos extracted from the client's 3x2 collage (504x504 each) | 6 x service-*.jpg | Done
31-Jul-2026 | 22:46 | Assets | Why Enpro icons extracted | Four brand icons cut from the client's icon sheet, background removed, recoloured for dark cards | 4 x icons/*.png | Done
31-Jul-2026 | 22:54 | Assets | Service detail icons extracted | Eight category icons extracted from the client's second icon sheet with transparency | 8 x icons/cat-*.png | Done
31-Jul-2026 | 18:39 | Assets | Banners and photos prepared | About Us banner, Services banner, office and contact photographs renamed and imported | 4 image files | Done
31-Jul-2026 | 22:55 | Development | Services data layer created | Central data file for all six services including full detail content for Structural Design & Engineering | src/data/services.ts | Done
31-Jul-2026 | 23:04 | Development | Routing restructured | New routes added for /about-us and /services/:slug; outdated /service-details route removed | src/App.tsx | Done
31-Jul-2026 | 23:50 | Development | Animation system set up | Framer Motion installed and shared motion presets created (fade, scale, stagger, scroll reveal) | src/lib/motion.ts | Done
01-Aug-2026 | 00:08 | Development | Landing page - Hero | New tagline and supporting line applied per client document; parallax zoom and staggered entrance added | src/components/Hero.tsx | Done
01-Aug-2026 | 00:34 | Development | Landing page - Why Enpro | Section renamed from Our Features; four new cards with client icons; modern dark glass cards on branded background | src/components/Services.tsx | Done
01-Aug-2026 | 00:46 | Development | Landing page - About | Heading changed to Engineering That Endures; three sub-points added; client office image applied | src/components/About.tsx | Done
01-Aug-2026 | 00:46 | Development | Landing page - Services | Six renamed services with new copy and editorial images; Show More toggle; distinct section styling | src/components/Feature.tsx | Done
01-Aug-2026 | 00:34 | Development | Landing page - Contact | New client image applied and service dropdown updated to the six current services | src/components/Contact.tsx | Done
01-Aug-2026 | 00:45 | Development | Footer rebuilt | Four column layout with new Contact column, light background, dark copyright strip | src/components/Footer.tsx | Done
01-Aug-2026 | 00:46 | Development | Sidebar navigation | Menu order updated per client; call to action and social icons restyled | src/components/Navbar.tsx | Done
01-Aug-2026 | 00:44 | Development | Brand social icons | Official solid brand marks created for LinkedIn, Facebook and WhatsApp | src/components/icons/SocialIcons.tsx | Done
01-Aug-2026 | 00:30 | Development | New page - Services detail | Full detail page built: What We Do (3x2 category grid + capability strip), How We Work, Project Impact | src/pages/ServiceDetail.tsx | Done
01-Aug-2026 | 00:20 | Development | New page - About Us | Full page built: About Enpro, Built to Evolve (editorial cards), Our Approach (timeline) | src/pages/AboutUs.tsx | Done
01-Aug-2026 | 00:15 | Development | Page banner component | Reusable banner with breadcrumb, matching the reference site's page header pattern | src/components/PageBanner.tsx | Done
01-Aug-2026 | 00:34 | Bug Fix | Footer logo broken in production | Logo used a hardcoded /src path that only resolves in development | src/components/Footer.tsx | Fixed
01-Aug-2026 | 00:34 | Bug Fix | Footer quick links not working | Link labels were lowercased into section ids that did not exist | src/components/Footer.tsx | Fixed
01-Aug-2026 | 00:34 | Bug Fix | Scroll snapping never active | Invalid Tailwind class snap-y-mandatory corrected to snap-y snap-proximity | src/pages/Index.tsx | Fixed
01-Aug-2026 | 00:34 | Bug Fix | Sidebar caused full page reload | Navigation used window.location.assign instead of in-page scrolling | src/components/Navbar.tsx | Fixed
01-Aug-2026 | 00:34 | Bug Fix | All services opened the same page | Every card linked to one static route; now routed per service slug | src/components/Feature.tsx | Fixed
01-Aug-2026 | 00:34 | Bug Fix | Undefined xs breakpoint | xs: classes were in use but never defined in the Tailwind config | tailwind.config.ts | Fixed
01-Aug-2026 | 00:46 | Bug Fix | Back to top inactive on detail pages | Component only listened to the landing page scroll container | src/components/ScrollToTop.tsx | Fixed
01-Aug-2026 | 00:34 | Responsive | Fluid typography system | clamp() based type scale added so headings scale smoothly at every resolution | tailwind.config.ts | Done
01-Aug-2026 | 00:34 | Responsive | Mobile viewport correction | Viewport heights switched to 100dvh so mobile browser chrome no longer clips content | Landing page sections | Done
01-Aug-2026 | 00:34 | Responsive | Consistent spacing scale | Section padding unified across all breakpoints | All landing sections | Done
01-Aug-2026 | 00:46 | Quality | Build and type check | Production build and TypeScript check passing with no errors | Whole project | Passed

## Pending Items
Item | What is needed | Why it is blocking | Owner
Logo source file | Vector or transparent PNG | The letter 'o' blends into the background because the current file is a JPEG | Client
Six service images | Separate high resolution files | Currently cropped from a single collage, which limits quality | Client
Contact form destination | Email address | The form currently shows a confirmation but does not send anything | Client
Social profile URLs | LinkedIn, Facebook, WhatsApp | All three links are placeholders | Client
Company contact details | Phone number and office address | Only the email address is available for the footer | Client
Hero background image | New photograph | Still the original placeholder image | Client
Favicon and share image | Brand assets | Still showing the Lovable platform placeholders | Client
Detail content - 5 services | Rev-B documents | Only Services-01 supplied; the other five show a Coming Soon state | Client
Navigation behaviour | Decision | Should sidebar 'About Us' scroll to the section or open the About Us page | Client
Three deviations from docs | Confirmation | 3 cards + Show More, hidden card headings, and left aligned text inside narrow cards | Client